## RAW_data
AreaCode | CountryCode | Subject | Problem_1 | Problem_2 | Problem_3 | Problem_4 | Problem_5 | Cause_1 | Cause_2 | Cause_3 | Cause_4 | Cause_5 | Effect_1 | Effect_2 | Effect_3 | Effect_4 | Effect_5 | Failure_1 | Failure_2 | Failure_3 | Failure_4 | Failure_5 | Mitigation_1 | Mitigation_2 | Mitigation_3 | Mitigation_4 | Mitigation_5
| IE | IE-5 | Communication flaws between us and the customer | Weak relationship to customer | Weak knowledge of customer's application domain | Communication flaws within the project team | Volatile customer's business domain regarding, e.g., changing points of contact, business processes or requirements | People assume day-to-day communication skills suffice when analysing complex business situations | Building rapport and good relationships with customers helps gain a better understanding of their requirements | Trying to understand what the needs of a business are without knowledge of area does not support good requirements understanding | Similar to first point - explaining, understanding complex problems is not an easy skill to acquire | Change is a reality. Without being adaptable, flexible and agile, IT solutions can become irrelevant | No good understanding of business needs, therefore IT solutions are waste of time | ditto | ditto | ditto | ditto | 1 | 0 | 0 | 0 | 0 | Concentrate skills on interpersonal, communication and analytical skills. | Ensure analysts have good interpersonal skills | Build understanding of business processes. Use system to help understand business context. | Good project leadership should help ensure regular communication between project team members | Adapt a flexible, agile approach. Understand 'Wicked Problem' and the skills needed to solved them - the answer to 'Cobb's Paradox'
| IE | IE-8 | Inconsistent requirements | Weak access to customer needs and / or (internal) business information | Insufficient support by customer | Time boxing / Not enough time in general | Underspecified requirements that are too abstract and allow for various interpretations | Customer wanting tighter controls/structure and extreme flexibility at the same time | Customer not appreciating the level of detail needed to define requirements | Not enough detail / background info provided | Fast paced change in customer's business environment not allowing for sufficient time to fully define requirements | Not enough time spent defining to the level of detail required | Difficult to meet requirements that contradict each other | Requirements poorly defined and product unlikely to suit at first attempt | Requirements poorly defined and product unlikely to suit at first attempt | Rushed development and requirements/processes can be missed if not defined properly | Requirements poorly defined and product unlikely to suit at first attempt | 0 | 0 | 1 | 1 | 0 | Persist in trying to define exact requirements with customer | Document gaps in understanding/requirements and try to remove them | Document gaps in understanding/requirements and try to remove them | Prioritise essential requirements and agree what may have to wait for a later implementation phase | Document gaps in understanding/requirements and try to remove them
| IE | IE-9 | Communication flaws between us and the customer | ^Gold plating^ (implementation of features without corresponding requirements) | Stakeholders with difficulties in separating requirements from previously known solution designs | Unclear / unmeasurable non-functional requirements | Moving targets (changing goals, business processes and / or requirements) | Cause_1: Not getting enough access to the PO's to discuss what is being built; Cause_2: Customer still have release dates but think all the users need everything at that date. This puts additional pressure on delivery teams; Cause_3: Stakeholder should be focused on goals and needs. The teams will work out the how, the stakeholder may choose and approach which is not the quickest to getting something out to the end user; Cause_4: Means Non functional requirements can not be signed off; Cause_5: Makes a set release date more difficult, and added pressure on delivery teams | 1 | 0 | 0 | 0 | 1
| IE | IE-10 | Time boxing / Not enough time in general | Moving targets (changing goals, business processes and / or requirements) | Volatile customer's business domain regarding, e.g., changing points of contact, business processes or requirements | Underspecified requirements that are too abstract and allow for various interpretations | Unclear responsibilities | Poor estimation, insufficient access to business Subject Matter Experts, delivery dates set in advance (before estimates) | Business/Customer not engaged and committed - have not thought the requirements through | Business/Customer not engaged and committed - not having the business/customer role and responsibilties properly defined and adhered to | Not enough time to flesh out requirements properly. Insufficient access to Subject Matter experts. | Lack of process definition and adherence. Lack of commitment from all stakeholders. | Coding will begin with poor quality requirements - potentially unclear or incomplete or wrong. Causes rework, waste and loss of morale. | Causes rework, waste and loss of morale. | Causes rework, waste and loss of morale. | Coding will begin with poor quality requirements - potentially unclear or incomplete or wrong. Causes rework, waste and loss of morale. Impacts further lifecycle phases downstream - e.g. test phase | Duplication of effort or something being missed altogether. Lack of review and sign-off process. No accountability if things go wrong. No commitment. | 0 | 1 | 0 | 0 | 0 | If we can, we will try and reduce scope. | Put focus on getting signed off requirements. | Putting focus on getting signed off requirements. Encouraging knowledge transfer when resources move on and off the project. | Use of change control. Reduce scope to later release if possible. | Trying to get roles and responsibilities clearly defined and agreed.
| IE | IE-12 | Communication flaws within the project team | Insufficient support by customer | Weak access to customer needs and / or (internal) business information | Moving targets (changing goals, business processes and / or requirements) | Time boxing / Not enough time in general | Distributed teams; one team may have people from India, UK, Boston and Seattle; No window when whole team is online at once. | New product so no existing customer base to reach out to; Also Sales and Support of similar products is the responsiblity by teams separate to the product development team so no direct customer relationship | Generally there will be only 2 people working on requirements on a teams servicing a team of 5-10 dev and 2-4 QA. Very little time to perform necessary research. | eCommerce is a very fluid domain. Customers' needs and demand change very quickly. | Requirements are discussed very early on before analysis has been completed. This means that they can sometimes have much greater impacts / complexities than first thought. | extra meetings needed to re-iterate discussions that have already happened |  | Develop products that are more technically pleasing than user friendly | A lot of time wasted understanding and estimating work that gets descoped. | The product backlog is used to capture small requirements that have fallen out of a previous release. Released features are not 100% but the remaining pieces never get prioritised as they are so small. | 0 | 0 | 1 | 1 | 0 | no mitigations | no mitigations | Rely heavily on the relevant domain experience of our Product Managers Business Analysts and UI designers for guidance. | At a certain sprint in a release, items for remaining sprints are locked down and only changed if approvals across all areas are obtained. | Have each mini feature prioritised within overall feature so that we deliver the highest priority items. Classify each mini feature as minimum ship Vs Stretch for the feature and ensure features are only released when their min ship criteria is released.
| IE | IE-13 | Stakeholders with difficulties in separating requirements from previously known solution designs | Time boxing / Not enough time in general | Moving targets (changing goals, business processes and / or requirements) | Terminological problems | Communication flaws between us and the customer | Lack of understanding of actual business need | Customer frustration | Development team frustration | Lack of understanding of actual business need | Lack of understanding of actual business need | Solution can be developed which in some cases may not be scalable and therefore involve more future investment | Solution can be rushed | Solution can be imcomplete |  |  | 0 | 0 | 1 | 0 | 1 | Enforce separation of solution and need/requirement | Replan at certain points if necessary | Replan at certain points if necessary and or prioritise
| IE | IE-14 | Communication flaws between us and the customer | Weak access to customer needs and / or (internal) business information | Discrepancy between high degree of innovation and need for formal acceptance of (potentially wrong / incomplete / unknown) requirements | Underspecified requirements that are too abstract and allow for various interpretations | Incomplete and / or hidden requirements | TIME ZONES | MULTIPLE LOCATIONS | GAPS BETWEEN INITIAL HIGH LEVEL DESIGN AND WAHTS FEASIBLE IN TIMEFRAMES | USE OF SEMI AGILE APPROACH | POOR UNDERSTANDING BY THE BA | DESIGN GAPS | DESGIN GAPS | DESIGN GAPS | DESIGN GAPS | REWORK POST IMP | 0 | 1 | 0 | 0 | 0 | SCRUMS | MULTIPLE WORKSHOPS | CHANGE CONTROL | DETAILED WIREFRAMES | BUSINESS REQUIREMENTS REVIEW AND SIGN-OFF
| IE | IE-15 | Weak access to customer needs and / or (internal) business information | Weak knowledge of customer's application domain | Communication flaws between us and the customer | Inconsistent requirements | ^Gold plating^ (implementation of features without corresponding requirements) | Difficult to get access to suitably diverse set of customers | The domain is not readily understood and needs access to experienced people | Development team tend to have proxy access to customer and therefore things get lost in translation | Changes or new thoughts can change requirements | Lack of understanding what real problem is or individuals pet ideas | Work on the wrong problem or not the root problem | Work on the wrong problem or not the root problem | Work on the wrong problem or not the root problem | Result in unnecessary change | Not working on solving the most valuable problems | 1 | 0 | 1 | 0 | 0
| IE | IE-16 | Weak knowledge of customer's application domain | Incomplete and / or hidden requirements | Moving targets (changing goals, business processes and / or requirements) | Discrepancy between high degree of innovation and need for formal acceptance of (potentially wrong / incomplete / unknown) requirements | Unclear / unmeasurable non-functional requirements | [10 empty] | 1 | 0 | 0 | 0 | 0
| IE | IE-17 | Terminological problems | Stakeholders with difficulties in separating requirements from previously known solution designs | ^Gold plating^ (implementation of features without corresponding requirements) | Communication flaws between us and the customer | Inconsistent requirements |  | loyalty to previously known solution | its only a simple quick change |  | definitions of requirements change over time | implementation differs from design | bias against the new system from project inception | can't test properly and not documented properly | each side getting annoyed with the other | frustration builds up in dev team | 0 | 0 | 0 | 1 | 1 | terminology section in docs | client management | nothing gets built without requirements | more frequent status meetings | requirements walk through sessions
| IE | IE-18 | Communication flaws between us and the customer | Communication flaws within the project team | Terminological problems | Incomplete and / or hidden requirements | ^Gold plating^ (implementation of features without corresponding requirements) | [10 empty] | 0 | 0 | 0 | 0 | 1
| IE | IE-21 | Inconsistent requirements | Communication flaws between us and the customer | Unclear responsibilities | Unclear / unmeasurable non-functional requirements | Weak relationship to customer | Different people writing requirements | Not enough customers willing to help out and also time constraints | No clear requirements process defined | Very hard to capture non-functional requirements | Not enough customers willing to help out and also time constraints | Leads to inconsistent projects, some projects work really well, others don't | We don't build what the customer wants | Project team not clear on who has to do what leading to missed requirements | Now this is resolved through regular playbacks but before this was done this led to not delivering what was expected | We don't build what the customer wants | 0 | 1 | 0 | 0 | 0 | None | None | None | Playbacks | None
| IE | IE-23 | Stakeholders with difficulties in separating requirements from previously known solution designs | Incomplete and / or hidden requirements | Underspecified requirements that are too abstract and allow for various interpretations |  |  | Stakeholders, from technical background find it a challenge to state the the what not the how. | Due to familiarity with a certain domain requirements can be short cut | Again general requirement statements are of little value without the user context |  |  | Lead to looking at the problem from an incorrect view point i.e. not the users | Incomplete requirements result in a poor experience for the user | Generic implementation of a feature will not meet the tailored needs of a user |  |  | 0 | 0 | 0 |  |  | Persona based conversations and no solution in the problem definition phase | Early demos and prototype to shorten the feedback loop to the user so path correction can be taken | In order to set context for as requirements, scenarios are used
| IE | IE-24 | Underspecified requirements that are too abstract and allow for various interpretations | ^Gold plating^ (implementation of features without corresponding requirements) | Unclear / unmeasurable non-functional requirements | Time boxing / Not enough time in general | Communication flaws within the project team | informal specifications | engineers have high (perfect) standards | difficult to define non-functional requirements to a number | estimates provided without fully understanding the feature/requirement | Everyone too busy with their own work | Rework | Features that are never used | Too little or too much effort spent on fulfilling | team frustration | rework | 0 | 1 | 0 | 0 | 0 | Written down and published | Encourage Minimim Viable Product (MVP) approach | Deine incremental metrics | Start with a discovery story before estimating | Daily Standup and Weekly Goal Review
| IE | IE-25 | Moving targets (changing goals, business processes and / or requirements) | Communication flaws between us and the customer | Incomplete and / or hidden requirements | Terminological problems | Time boxing / Not enough time in general | senior management confusion/churn | lack of access to real customer, conversation mediated by sales people | too little analysis at the outset | use of broad terms such as orchestration | as much a matter of resource contention as time. over commitment in effect | obvious | obvious | obvious | obvious | obvious | 0 | 1 | 0 | 0 | 1 | none, we just roll with it | we push for agile and involvement of customer in scrum teams | more analysis before commitment, or adoption of agile rather than fixed price/scope | definitions at the outset | none - fact of life.
| IE | IE-26 | Communication flaws within the project team | [14 empty] | 0
| IE | IE-27 | Moving targets (changing goals, business processes and / or requirements) | Weak access to customer needs and / or (internal) business information | Communication flaws between us and the customer | Underspecified requirements that are too abstract and allow for various interpretations | Incomplete and / or hidden requirements | customers unsure of what thaye want/what is possible | customers do not want to cooperate or be onsite or are too busy | Cant get hold of key customers | The customer states no preference in sopme cases | Surpises that come well after start - customer forgets to mention something | rework | rework | rework and fallout with customer | extra effort unplanned | extra work during development | 1 | 1 | 0 | 0 | 0 | customer contracted to attend project meetings at least once per week to clarify things | customer contracted to attend project meetings at least once per week to clarify things | customer contracted to attend project meetings at least once per week to clarify things | contract is short term - small releases small mini contracts | no mitigations - just live with it/ overprice work to allow for this
| IE | IE-28 | Unclear / unmeasurable non-functional requirements | Underspecified requirements that are too abstract and allow for various interpretations | Volatile customer's business domain regarding, e.g., changing points of contact, business processes or requirements | Communication flaws within the project team | Terminological problems | scope creep | scope creep | communication issues | misintrepretations | scope creep | strained relationships | strained relationships | strained relationships | strained relationships | strained relationships | 0 | 1 | 0 | 0 | 0 | regular project meetings | regular project meetings | regular project meetings | regular project meetings | regular project meetings

## coding
AreaCode | CountryCode | Subject | Coded | Validated | Communication flaws within the project team | Communication flaws between us and the customer | Terminological problems | Unclear responsibilities | Incomplete and / or hidden requirements | Insufficient support by project lead | Insufficient support by customer | Stakeholders with difficulties in separating requirements from previously known solution designs | Inconsistent requirements | Missing traceability | Moving targets (changing goals, business processes and / or requirements) | ^Gold plating^ (implementation of features without corresponding requirements) | Weak access to customer needs and / or (internal) business information | Weak knowledge of customer's application domain | Weak relationship to customer | Time boxing / Not enough time in general | Discrepancy between high degree of innovation and need for formal acceptance of (potentially wrong / incomplete / unknown) requirements | Technically unfeasible requirements | Underspecified requirements that are too abstract and allow for various interpretations | Unclear / unmeasurable non-functional requirements | Volatile customer's business domain regarding, e.g., changing points of contact, business processes or requirements | Causes.Original.Statements | Effects.Original.Statements | Project.Failure.0.1 | Mitigation.Original.Statements
| IE | IE-5 |  |  |  | YES | [19 empty] | People assume day-to-day communication skills suffice when analysing complex business situations | No good understanding of business needs, therefore IT solutions are waste of time | 1 | Concentrate skills on interpersonal, communication and analytical skills.
| IE | IE-5 | [16 empty] | YES | [6 empty] | Building rapport and good relationships with customers helps gain a better understanding of their requirements | ditto | 0 | Ensure analysts have good interpersonal skills
| IE | IE-5 | [15 empty] | YES | [7 empty] | Trying to understand what the needs of a business are without knowledge of area does not support good requirements understanding | ditto | 0 | Build understanding of business processes. Use system to help understand business context.
| IE | IE-5 |  |  | YES | [20 empty] | Similar to first point - explaining, understanding complex problems is not an easy skill to acquire | ditto | 0 | Good project leadership should help ensure regular communication between project team members
| IE | IE-5 | [22 empty] | YES | Change is a reality. Without being adaptable, flexible and agile, IT solutions can become irrelevant | ditto | 0 | Adapt a flexible, agile approach. Understand 'Wicked Problem' and the skills needed to solved them - the answer to 'Cobb's Paradox'
| IE | IE-8 | [10 empty] | YES | [12 empty] | Customer wanting tighter controls/structure and extreme flexibility at the same time | Difficult to meet requirements that contradict each other | 0 | Persist in trying to define exact requirements with customer
| IE | IE-8 | [14 empty] | YES | [8 empty] | Customer not appreciating the level of detail needed to define requirements | Requirements poorly defined and product unlikely to suit at first attempt | 0 | Document gaps in understanding/requirements and try to remove them
| IE | IE-8 | [8 empty] | YES | [14 empty] | Not enough detail / background info provided | Requirements poorly defined and product unlikely to suit at first attempt | 1 | Document gaps in understanding/requirements and try to remove them
| IE | IE-8 | [17 empty] | YES | [5 empty] | Fast paced change in customer's business environment not allowing for sufficient time to fully define requirements | Rushed development and requirements/processes can be missed if not defined properly | 1 | Prioritise essential requirements and agree what may have to wait for a later implementation phase
| IE | IE-8 | [20 empty] | YES |  |  | Not enough time spent defining to the level of detail required | Requirements poorly defined and product unlikely to suit at first attempt | 0 | Document gaps in understanding/requirements and try to remove them
| IE | IE-9 |  |  |  | YES | [19 empty] | Not getting enough access to the PO's to discuss what is being built |  | 1
| IE | IE-9 | [13 empty] | YES | [9 empty] | Customer still have release dates but think all the users need everything at that date. This puts additional pressure on delivery teams |  | 0
| IE | IE-9 | [9 empty] | YES | [13 empty] | Stakeholder should be focused on goals and needs. The teams will work out the how, the stakeholder may choose and approach which is not the quickest to getting something out to the end user |  | 0
| IE | IE-9 | [21 empty] | YES |  | Means Non functional requirements can not be signed off |  | 0
| IE | IE-9 | [12 empty] | YES | [10 empty] | Makes a set release date more difficult, and added pressure on delivery teams |  | 1
| IE | IE-10 | [17 empty] | YES | [5 empty] | Poor estimation, insufficient access to business Subject Matter Experts, delivery dates set in advance (before estimates) | Coding will begin with poor quality requirements - potentially unclear or incomplete or wrong. Causes rework, waste and loss of morale. | 0 | If we can, we will try and reduce scope.
| IE | IE-10 | [12 empty] | YES | [10 empty] | Business/Customer not engaged and committed - have not thought the requirements through | Causes rework, waste and loss of morale. | 1 | Put focus on getting signed off requirements.
| IE | IE-10 | [22 empty] | YES | Business/Customer not engaged and committed - not having the business/customer role and responsibilties properly defined and adhered to | Causes rework, waste and loss of morale. | 0 | Putting focus on getting signed off requirements. Encouraging knowledge transfer when resources move on and off the project.
| IE | IE-10 | [20 empty] | YES |  |  | Not enough time to flesh out requirements properly. Insufficient access to Subject Matter experts. | Coding will begin with poor quality requirements - potentially unclear or incomplete or wrong. Causes rework, waste and loss of morale. Impacts further lifecycle phases downstream - e.g. test phase | 0 | Use of change control. Reduce scope to later release if possible.
| IE | IE-10 | [5 empty] | YES | [17 empty] | Lack of process definition and adherence. Lack of commitment from all stakeholders. | Duplication of effort or something being missed altogether. Lack of review and sign-off process. No accountability if things go wrong. No commitment. | 0 | Trying to get roles and responsibilities clearly defined and agreed.
| IE | IE-12 |  |  | YES | [20 empty] | Distributed teams; one team may have people from India, UK, Boston and Seattle; No window when whole team is online at once. | extra meetings needed to re-iterate discussions that have already happened | 0 | no mitigations
| IE | IE-12 | [8 empty] | YES | [14 empty] | New product so no existing customer base to reach out to; Also Sales and Support of similar products is the responsiblity by teams separate to the product development team so no direct customer relationship |  | 0 | no mitigations
| IE | IE-12 | [14 empty] | YES | [8 empty] | Generally there will be only 2 people working on requirements on a teams servicing a team of 5-10 dev and 2-4 QA. Very little time to perform necessary research. | Develop products that are more technically pleasing than user friendly | 1 | Rely heavily on the relevant domain experience of our Product Managers Business Analysts and UI designers for guidance.
| IE | IE-12 | [12 empty] | YES | [10 empty] | eCommerce is a very fluid domain. Customers' needs and demand change very quickly. | A lot of time wasted understanding and estimating work that gets descoped. | 1 | At a certain sprint in a release, items for remaining sprints are locked down and only changed if approvals across all areas are obtained.
| IE | IE-12 | [17 empty] | YES | [5 empty] | Requirements are discussed very early on before analysis has been completed. This means that they can sometimes have much greater impacts / complexities than first thought. | The product backlog is used to capture small requirements that have fallen out of a previous release. Released features are not 100% but the remaining pieces never get prioritised as they are so small. | 0 | Have each mini feature prioritised within overall feature so that we deliver the highest priority items. Classify each mini feature as minimum ship Vs Stretch for the feature and ensure features are only released when their min ship criteria is released.
| IE | IE-13 | [9 empty] | YES | [13 empty] | Lack of understanding of actual business need | Solution can be developed which in some cases may not be scalable and therefore involve more future investment | 0 | Enforce separation of solution and need/requirement
| IE | IE-13 | [17 empty] | YES | [5 empty] | Customer frustration | Solution can be rushed | 0 | Replan at certain points if necessary
| IE | IE-13 | [12 empty] | YES | [10 empty] | Development team frustration | Solution can be imcomplete | 1 | Replan at certain points if necessary and or prioritise
| IE | IE-13 |  |  |  |  | YES | [18 empty] | Lack of understanding of actual business need |  | 0
| IE | IE-13 |  |  |  | YES | [19 empty] | Lack of understanding of actual business need |  | 1
| IE | IE-14 |  |  |  | YES | [19 empty] | TIME ZONES | DESIGN GAPS | 0 | SCRUMS
| IE | IE-14 | [14 empty] | YES | [8 empty] | MULTIPLE LOCATIONS | DESGIN GAPS | 1 | MULTIPLE WORKSHOPS
| IE | IE-14 | [18 empty] | YES |  |  |  |  | GAPS BETWEEN INITIAL HIGH LEVEL DESIGN AND WAHTS FEASIBLE IN TIMEFRAMES | DESIGN GAPS | 0 | CHANGE CONTROL
| IE | IE-14 | [20 empty] | YES |  |  | USE OF SEMI AGILE APPROACH | DESIGN GAPS | 0 | DETAILED WIREFRAMES
| IE | IE-14 | [6 empty] | YES | [16 empty] | POOR UNDERSTANDING BY THE BA | REWORK POST IMP | 0 | BUSINESS REQUIREMENTS REVIEW AND SIGN-OFF
| IE | IE-15 | [14 empty] | YES | [8 empty] | Difficult to get access to suitably diverse set of customers | Work on the wrong problem or not the root problem | 1
| IE | IE-15 | [15 empty] | YES | [7 empty] | The domain is not readily understood and needs access to experienced people | Work on the wrong problem or not the root problem | 0
| IE | IE-15 |  |  |  | YES | [19 empty] | Development team tend to have proxy access to customer and therefore things get lost in translation | Work on the wrong problem or not the root problem | 1
| IE | IE-15 | [10 empty] | YES | [12 empty] | Changes or new thoughts can change requirements | Result in unnecessary change | 0
| IE | IE-15 | [13 empty] | YES | [9 empty] | Lack of understanding what real problem is or individuals pet ideas | Not working on solving the most valuable problems | 0
| IE | IE-16 | [15 empty] | YES | [9 empty] | 1
| IE | IE-16 | [6 empty] | YES | [18 empty] | 0
| IE | IE-16 | [12 empty] | YES | [12 empty] | 0
| IE | IE-16 | [18 empty] | YES | [6 empty] | 0
| IE | IE-16 | [21 empty] | YES |  |  |  | 0
| IE | IE-17 |  |  |  |  | YES | [19 empty] | implementation differs from design | 0 | terminology section in docs
| IE | IE-17 | [9 empty] | YES | [13 empty] | loyalty to previously known solution | bias against the new system from project inception | 0 | client management
| IE | IE-17 | [13 empty] | YES | [9 empty] | its only a simple quick change | can't test properly and not documented properly | 0 | nothing gets built without requirements
| IE | IE-17 |  |  |  | YES | [20 empty] | each side getting annoyed with the other | 1 | more frequent status meetings
| IE | IE-17 | [10 empty] | YES | [12 empty] | definitions of requirements change over time | frustration builds up in dev team | 1 | requirements walk through sessions
| IE | IE-18 |  |  |  | YES | [21 empty] | 0
| IE | IE-18 |  |  | YES | [22 empty] | 0
| IE | IE-18 |  |  |  |  | YES | [20 empty] | 0
| IE | IE-18 | [6 empty] | YES | [18 empty] | 0
| IE | IE-18 | [13 empty] | YES | [11 empty] | 1
| IE | IE-21 | [10 empty] | YES | [12 empty] | Different people writing requirements | Leads to inconsistent projects, some projects work really well, others don't | 0 | None
| IE | IE-21 |  |  |  | YES | [19 empty] | Not enough customers willing to help out and also time constraints | We don't build what the customer wants | 1 | None
| IE | IE-21 | [5 empty] | YES | [17 empty] | No clear requirements process defined | Project team not clear on who has to do what leading to missed requirements | 0 | None
| IE | IE-21 | [21 empty] | YES |  | Very hard to capture non-functional requirements | Now this is resolved through regular playbacks but before this was done this led to not delivering what was expected | 0 | Playbacks
| IE | IE-21 | [16 empty] | YES | [6 empty] | Not enough customers willing to help out and also time constraints | We don't build what the customer wants | 0 | None
| IE | IE-23 | [9 empty] | YES | [13 empty] | Stakeholders, from technical background find it a challenge to state the the what not the how. | Lead to looking at the problem from an incorrect view point i.e. not the users | 0 | Persona based conversations and no solution in the problem definition phase
| IE | IE-23 | [6 empty] | YES | [16 empty] | Due to familiarity with a certain domain requirements can be short cut | Incomplete requirements result in a poor experience for the user | 0 | Early demos and prototype to shorten the feedback loop to the user so path correction can be taken
| IE | IE-23 | [20 empty] | YES |  |  | Again general requirement statements are of little value without the user context | Generic implementation of a feature will not meet the tailored needs of a user | 0 | In order to set context for as requirements, scenarios are used
| IE | IE-23
| IE | IE-23
| IE | IE-24 | [20 empty] | YES |  |  | informal specifications | Rework | 0 | Written down and published
| IE | IE-24 | [13 empty] | YES | [9 empty] | engineers have high (perfect) standards | Features that are never used | 1 | Encourage Minimim Viable Product (MVP) approach
| IE | IE-24 | [21 empty] | YES |  | difficult to define non-functional requirements to a number | Too little or too much effort spent on fulfilling | 0 | Deine incremental metrics
| IE | IE-24 | [17 empty] | YES | [5 empty] | estimates provided without fully understanding the feature/requirement | team frustration | 0 | Start with a discovery story before estimating
| IE | IE-24 |  |  | YES | [20 empty] | Everyone too busy with their own work | rework | 0 | Daily Standup and Weekly Goal Review
| IE | IE-25 | [12 empty] | YES | [10 empty] | senior management confusion/churn | obvious | 0 | none, we just roll with it
| IE | IE-25 |  |  |  | YES | [19 empty] | lack of access to real customer, conversation mediated by sales people | obvious | 1 | we push for agile and involvement of customer in scrum teams
| IE | IE-25 | [6 empty] | YES | [16 empty] | too little analysis at the outset | obvious | 0 | more analysis before commitment, or adoption of agile rather than fixed price/scope
| IE | IE-25 |  |  |  |  | YES | [18 empty] | use of broad terms such as orchestration | obvious | 0 | definitions at the outset
| IE | IE-25 | [17 empty] | YES | [5 empty] | as much a matter of resource contention as time. over commitment in effect | obvious | 1 | none - fact of life.
| IE | IE-26 |  |  | YES | [22 empty] | 0
| IE | IE-26
| IE | IE-26
| IE | IE-26
| IE | IE-26
| IE | IE-27 | [12 empty] | YES | [10 empty] | customers unsure of what thaye want/what is possible | rework | 1 | customer contracted to attend project meetings at least once per week to clarify things
| IE | IE-27 | [14 empty] | YES | [8 empty] | customers do not want to cooperate or be onsite or are too busy | rework | 1 | customer contracted to attend project meetings at least once per week to clarify things
| IE | IE-27 |  |  |  | YES | [19 empty] | Cant get hold of key customers | rework and fallout with customer | 0 | customer contracted to attend project meetings at least once per week to clarify things
| IE | IE-27 | [20 empty] | YES |  |  | The customer states no preference in sopme cases | extra effort unplanned | 0 | contract is short term - small releases small mini contracts
| IE | IE-27 | [6 empty] | YES | [16 empty] | Surpises that come well after start - customer forgets to mention something | extra work during development | 0 | no mitigations - just live with it/ overprice work to allow for this
| IE | IE-28 | [21 empty] | YES |  | scope creep | strained relationships | 0 | regular project meetings
| IE | IE-28 | [20 empty] | YES |  |  | scope creep | strained relationships | 1 | regular project meetings
| IE | IE-28 | [22 empty] | YES | communication issues | strained relationships | 0 | regular project meetings
| IE | IE-28 |  |  | YES | [20 empty] | misintrepretations | strained relationships | 0 | regular project meetings
| IE | IE-28 |  |  |  |  | YES | [18 empty] | scope creep | strained relationships | 0 | regular project meetings