## RAW_data
AreaCode | CountryCode | Subject | Problem_1 | Problem_2 | Problem_3 | Problem_4 | Problem_5 | Cause_1 | Cause_2 | Cause_3 | Cause_4 | Cause_5 | Effect_1 | Effect_2 | Effect_3 | Effect_4 | Effect_5 | Failure_1 | Failure_2 | Failure_3 | Failure_4 | Failure_5 | Mitigation_1 | Mitigation_2 | Mitigation_3 | Mitigation_4 | Mitigation_5
| NO | NO-1 | Communication flaws between us and the customer | Stakeholders with difficulties in separating requirements from previously known solution designs | Communication flaws between us and the customer | Incomplete and / or hidden requirements | Incomplete and / or hidden requirements | [10 empty] | 0 | 0 | 0 | 0 | 0
| NO | NO-2 | Underspecified requirements that are too abstract and allow for various interpretations | Weak knowledge of customer's application domain | Incomplete and / or hidden requirements | Missing traceability | Terminological problems | When definining requirements the author often expects the reader to have the same domain knowledge and expertise as herself. | Aquiring knowledge and understand the business process take long time; much more time than is available. Developers are interested in technology not business | RE expects the reader to have more domain knowledge than they actually have. | Lack of good tool support | Domain experts use domain specific terminology and IT specialist use IT related terminology | Functionality has to be reimplemented and retested when misunderstandings have been clarified. | Not able to prioritze most critical functionality; not able to distinguish between critical and non-critiacal functionalty | Missing functionality; additional time and cost needed | When changes are introduced during testing it is hard to find out whether it is a bug or change | Leads to misunderstandings because stakeholders and developers use different terminologies | 1 | 1 | 0 | 0 | 0
| NO | NO-6 | Communication flaws between us and the customer | Weak access to customer needs and / or (internal) business information | Weak knowledge of customer's application domain | Stakeholders with difficulties in separating requirements from previously known solution designs | Insufficient support by customer | Weak conceptualization / visualization of the solution | No clear responsibility for customer / stakeholder needs | Engineers do not have usage experience and are not educated there in | We interview / ask rather than observe | No clear responsibility for customer / stakeholder needs | We do not develop the right product | We do not develop the right product | We do not develop the right product | We are note innovative enough | We do not develop the right product | 1 | 1 | 1 | 0 | 0 | improve how we conceptualize (visualize) the solution and main product characteristics | Institue a clear product owner role that acts as a proxy for the customer | Educate engineers in the stekeholders use of the product | Observe users rather than asking | Institue a clear product owner role that acts as a proxy for the customer
| NO | NO-8 | Time boxing / Not enough time in general | Incomplete and / or hidden requirements | Moving targets (changing goals, business processes and / or requirements) | Underspecified requirements that are too abstract and allow for various interpretations | Communication flaws between us and the customer | Cause_1: money; Cause_2: money; Cause_3: money; Cause_4: money; Cause_5: money | 0 | 0 | 0 | 0 | 0
| NO | NO-9 | Communication flaws within the project team | Moving targets (changing goals, business processes and / or requirements) | Terminological problems | Unclear / unmeasurable non-functional requirements | Stakeholders with difficulties in separating requirements from previously known solution designs | [10 empty] | 1 | 1 | 0 | 0 | 0
| NO | NO-10 | Weak access to customer needs and / or (internal) business information | Moving targets (changing goals, business processes and / or requirements) | Weak access to customer needs and / or (internal) business information | Unclear responsibilities | Incomplete and / or hidden requirements | Many buisiness layers between customer and development department | Requirements not always frosen at the time developmnt is started | Many buisiness layers between customer and development department | Responsibilities that involves two domains (eg. electronic and embedded SW) | Prerequisites for the main requirements | Requirements communicated throug the organization may end up to not be what the customer wanted | Longer development time | Requirements communicated throug the organization may end up to not be what the customer wanted | longer development time | Budget estimates may be unbcorrect due to more work needed than first expected | 0 | 1 | 0 | 0 | 0 | Communication directly with the people talking to the customer | Freeze requirements early | Requirements communicated throug the organization may end up to not be what the customer wanted | Clarify responsibility | Analyze the requirements more thorough before starting the development
| NO | NO-12 | Communication flaws between us and the customer | Terminological problems | Incomplete and / or hidden requirements | Insufficient support by customer | Communication flaws within the project team | Use of a language specific of the problem domain often leads to some misunderstanding | Same as above. Need of a common, shared vocabulary | Customers tend to underestimate the complexity of the problem | After the initial meetings, usually, they don't plan carefully the resources needed from their side to support the project during its whole lifetime | Business analysts and developers don't share the same language | Delays, cost increases | Wrong implementations | Delays, cost increases | Difficulties in testing the system | Bad planning | 1 | 0 | 0 | 0 | 0 | Share as much as possible the requirements and their specification with the customer. Making them understandable to a non technical audience | Adoption of a shared glossary, interviews... |  |  | Meetings, meetings, .... meetings
| NO | NO-15 | Communication flaws within the project team | Unclear responsibilities | Stakeholders with difficulties in separating requirements from previously known solution designs |  |  | Cause_1: Our developers don't know the flows to generate questions to other teams.; Cause_2: Our developers did not involve in the developement process; Cause_3: The Stakeholders don't have well knowledge about the technical issues related with their requirements; Effect_1: we waste time trying to develop new features that were developed by other teams previously; Effect_2: when we need modify or fix some feature we waste time trying to understand how to do it | 1 | 1 | 0 |  |  | we defined one member in charge to the communication with other teams | we splited the dev team in two small teams with clear responsibilities
| NO | NO-20 | Incomplete and / or hidden requirements | Stakeholders with difficulties in separating requirements from previously known solution designs | Time boxing / Not enough time in general | Moving targets (changing goals, business processes and / or requirements) | Communication flaws between us and the customer | [10 empty] | 1 | 1 | 1 | 0 | 0
| NO | NO-21 | Communication flaws between us and the customer | Unclear responsibilities | Insufficient support by project lead | Insufficient support by customer | Communication flaws within the project team | [10 empty] | 1 | 1 | 1 | 1 | 0

## coding
AreaCode | CountryCode | Subject | Coded | Validated | Communication flaws within the project team | Communication flaws between us and the customer | Terminological problems | Unclear responsibilities | Incomplete and / or hidden requirements | Insufficient support by project lead | Insufficient support by customer | Stakeholders with difficulties in separating requirements from previously known solution designs | Inconsistent requirements | Missing traceability | Moving targets (changing goals, business processes and / or requirements) | "Gold plating" (implementation of features without corresponding requirements) | Weak access to customer needs and / or (internal) business information | Weak knowledge of customer's application domain | Weak relationship to customer | Time boxing / Not enough time in general | Discrepancy between high degree of innovation and need for formal acceptance of (potentially wrong / incomplete / unknown) requirements | Technically unfeasible requirements | Underspecified requirements that are too abstract and allow for various interpretations | Unclear / unmeasurable non-functional requirements | Volatile customer's business domain regarding, e.g., changing points of contact, business processes or requirements | Causes.Original.Statements | Effects.Original.Statements | Project.Failure.0.1 | Mitigation.Original.Statements
| NO | NO-1 |  |  |  | YES | [21 empty] | 0
| NO | NO-1 | [9 empty] | YES | [15 empty] | 0
| NO | NO-1 |  |  |  | YES | [21 empty] | 0
| NO | NO-1 | [6 empty] | YES | [18 empty] | 0
| NO | NO-1 | [6 empty] | YES | [18 empty] | 0
| NO | NO-2 | [20 empty] | YES |  |  | When definining requirements the author often expects the reader to have the same domain knowledge and expertise as herself. | Functionality has to be reimplemented and retested when misunderstandings have been clarified. | 1
| NO | NO-2 | [15 empty] | YES | [7 empty] | Aquiring knowledge and understand the business process take long time; much more time than is available. Developers are interested in technology not business | Not able to prioritze most critical functionality; not able to distinguish between critical and non-critiacal functionalty | 1
| NO | NO-2 | [6 empty] | YES | [16 empty] | RE expects the reader to have more domain knowledge than they actually have. | Missing functionality; additional time and cost needed | 0
| NO | NO-2 | [11 empty] | YES | [11 empty] | Lack of good tool support | When changes are introduced during testing it is hard to find out whether it is a bug or change | 0
| NO | NO-2 |  |  |  |  | YES | [18 empty] | Domain experts use domain specific terminology and IT specialist use IT related terminology | Leads to misunderstandings because stakeholders and developers use different terminologies | 0
| NO | NO-6 |  |  |  | YES | [19 empty] | Weak conceptualization / visualization of the solution | We do not develop the right product | 1 | improve how we conceptualize (visualize) the solution and main product characteristics
| NO | NO-6 | [14 empty] | YES | [8 empty] | No clear responsibility for customer / stakeholder needs | We do not develop the right product | 1 | Institue a clear product owner role that acts as a proxy for the customer
| NO | NO-6 | [15 empty] | YES | [7 empty] | Engineers do not have usage experience and are not educated there in | We do not develop the right product | 1 | Educate engineers in the stekeholders use of the product
| NO | NO-6 | [9 empty] | YES | [13 empty] | We interview / ask rather than observe | We are note innovative enough | 0 | Observe users rather than asking
| NO | NO-6 | [8 empty] | YES | [14 empty] | No clear responsibility for customer / stakeholder needs | We do not develop the right product | 0 | Institue a clear product owner role that acts as a proxy for the customer
| NO | NO-8 | [17 empty] | YES | [5 empty] | money |  | 0
| NO | NO-8 | [6 empty] | YES | [16 empty] | money |  | 0
| NO | NO-8 | [12 empty] | YES | [10 empty] | money |  | 0
| NO | NO-8 | [20 empty] | YES |  |  | money |  | 0
| NO | NO-8 |  |  |  | YES | [19 empty] | money |  | 0
| NO | NO-9 |  |  | YES | [22 empty] | 1
| NO | NO-9 | [12 empty] | YES | [12 empty] | 1
| NO | NO-9 |  |  |  |  | YES | [20 empty] | 0
| NO | NO-9 | [21 empty] | YES |  |  |  | 0
| NO | NO-9 | [9 empty] | YES | [15 empty] | 0
| NO | NO-10 | [14 empty] | YES | [8 empty] | Many buisiness layers between customer and development department | Requirements communicated throug the organization may end up to not be what the customer wanted | 0 | Communication directly with the people talking to the customer
| NO | NO-10 | [12 empty] | YES | [10 empty] | Requirements not always frosen at the time developmnt is started | Longer development time | 1 | Freeze requirements early
| NO | NO-10 | [14 empty] | YES | [8 empty] | Many buisiness layers between customer and development department | Requirements communicated throug the organization may end up to not be what the customer wanted | 0 | Requirements communicated throug the organization may end up to not be what the customer wanted
| NO | NO-10 | [5 empty] | YES | [17 empty] | Responsibilities that involves two domains (eg. electronic and embedded SW) | longer development time | 0 | Clarify responsibility
| NO | NO-10 | [6 empty] | YES | [16 empty] | Prerequisites for the main requirements | Budget estimates may be unbcorrect due to more work needed than first expected | 0 | Analyze the requirements more thorough before starting the development
| NO | NO-12 |  |  |  | YES | [19 empty] | Use of a language specific of the problem domain often leads to some misunderstanding | Delays, cost increases | 1 | Share as much as possible the requirements and their specification with the customer. Making them understandable to a non technical audience
| NO | NO-12 |  |  |  |  | YES | [18 empty] | Same as above. Need of a common, shared vocabulary | Wrong implementations | 0 | Adoption of a shared glossary, interviews...
| NO | NO-12 | [6 empty] | YES | [16 empty] | Customers tend to underestimate the complexity of the problem | Delays, cost increases | 0
| NO | NO-12 | [8 empty] | YES | [14 empty] | After the initial meetings, usually, they don't plan carefully the resources needed from their side to support the project during its whole lifetime | Difficulties in testing the system | 0
| NO | NO-12 |  |  | YES | [20 empty] | Business analysts and developers don't share the same language | Bad planning | 0 | Meetings, meetings, .... meetings
| NO | NO-15 |  |  | YES | [20 empty] | Our developers don't know the flows to generate questions to other teams. | we waste time trying to develop new features that were developed by other teams previously | 1 | we defined one member in charge to the communication with other teams
| NO | NO-15 | [5 empty] | YES | [17 empty] | Our developers did not involve in the developement process | when we need modify or fix some feature we waste time trying to understand how to do it | 1 | we splited the dev team in two small teams with clear responsibilities
| NO | NO-15 | [9 empty] | YES | [13 empty] | The Stakeholders don't have well knowledge about the technical issues related with their requirements |  | 0
| NO | NO-15
| NO | NO-15
| NO | NO-20 | [6 empty] | YES | [18 empty] | 1
| NO | NO-20 | [9 empty] | YES | [15 empty] | 1
| NO | NO-20 | [17 empty] | YES | [7 empty] | 1
| NO | NO-20 | [12 empty] | YES | [12 empty] | 0
| NO | NO-20 |  |  |  | YES | [21 empty] | 0
| NO | NO-21 |  |  |  | YES | [21 empty] | 1
| NO | NO-21 | [5 empty] | YES | [19 empty] | 1
| NO | NO-21 | [7 empty] | YES | [17 empty] | 1
| NO | NO-21 | [8 empty] | YES | [16 empty] | 1
| NO | NO-21 |  |  | YES | [22 empty] | 0